## Project Management
Project Name : Kewal Endoscopy Center (KEC)
Project Type | Web Site (Responsive, Static)
Project Detail | Date
Project Start Date | 2015-12-29
Project End Date
Release 1 - Demo | 2016-01-11
Release 2 - First Domain Deployment

## Resource Management
Category | Resource Name
Web Devlopement | Veena
Review | Ameer
UI Modification | Ameer
Change Request | Mubasshir
Bug Fixes
``

## CR Management
CR Date : 23/01/2016
CR Name | Description | Page/Change Area | Resource | Start Date | End Date | Actual Start Date | Actual End Date | Status | Comments
Text Removal and UI Modification | "We are Kewal Endoscopy Center (bold pink) located in Jalgaon, Maharashtra, specializing in Gynecological laparoscopy, hysteroscopy & infertility. (REMOVE -> )We are licensed by the State of Maharashtra and the Centers for Medicare and Medicaid." | Home Page | Mubasshir | 2016-01-30 | 2016-01-30 |  | 2016-02-02 | Completed
Text Modification | Doctor's Profile : * - Consultant Laparoscopy Surgeon* | Home Page | Mubasshir | 2016-01-30 | 2016-01-30 |  | 2015-12-31 | Completed
Text Removal | (Remove ->) "training schedules for young Endoscopists are also available at the clinic." | About Us | Mubasshir | 2016-01-30 | 2016-01-30 |  | 2015-12-31 | Completed
Menu Removal | (Remove->) All info about ART | Top Navigation | Mubasshir | 2016-01-31 | 2016-01-31 |  | 2016-02-02 | Completed
Menu Addition | Add new Menu : FAQ's and Add all FAQ's from http://laparoscopyexpert.com/faq_for_patient.html (Ameer: As per the Testimonials page) | Top Navigation | Mubasshir and Veena | 2016-02-01 | 2016-02-03 |  | 2016-02-05 | Completed

## To-Do Tasks
Page | Task | Category | Resource | Completion Date | Status
About Us | This page contains Photo Gallery with Dummy Data. Need to put actual data. | Data |  |  | Not Started
News and Press | There are some dummy news and dummy archives on Right Side bar. Need to put actual data. | Data |  |  | Not Started
Testimonials | Contains dummy data. Need to replace with the actual one. | Data |  |  | Not Started
Videos | Contains dummy videos. Need to replace with the actual one. | Data |  |  | Not Started
FAQ | 1. Add FAQ's from : http://laparoscopyexpert.com/faq_for_patient.html 2. Remove "For patients" & show directly under FAQ's (Ameer) | CR | Mubasshir and Veena | 2016-02-05 | Completed
Footer | remove the links for "PINTEREST" and "RSS". Keep only FB, Twitter, & LinkedIn. | CR | Veena |  | In Progress
Contact US | Current Code is not working. We'll actually deploy & will check if existing code works or not. |  |  |  | Not Started
All Pages | Minimize the white space in top bar (Ameer) | UI Modification | Veena | 2016-02-05 | Completed
All Pages | Change background color of "Read More" or any other relevant component from blue to Dark Pink & & use label color as white for same. (Ameer) | UI Modification | Veena | 2016-02-05 | Completed
All Pages | Could see significant blank space on top of actual page design of all pages. For e.g. just see above "Home / About Us" text on about us page. (Ameer) | UI Modification | Veena | 2016-02-05 | Completed
All Pages | Color of "Home / Meet the Doctor" should get changed to "Home (dark pink used in app)/ Meet the Doctor" (Ameer) | UI Modification | Veena | 2016-02-05 | Completed
Services | On Services main page link for "Infertility" is missing in page. As of now only two links are provided. (Ameer) | Defect | Veena | 2016-02-05 | Completed
Top Navigation - Services | On Services drop down if I select "Infertility" it doesn't move to that page. It should navigate to overview page. (Ameer) | Defect | Veena | 2016-02-05 | Completed
Breadcrumb | On selection of any navigation item it starts with "Home / Meet the Doctor". Rather it should start with actual navigation item for e.g "About Us / Meet the Doctor". (Ameer) | Defect | Veena | 2016-02-05 | Completed
All Pages | Integration of Actual KEC Images | Data | Veena |  | Not Started
Note on F8: Author: Need actua links for twitter and linkedin