## Project Management
Project Name : Kewal Endoscopy Center (KEC)
Project Type | Web Site (Responsive, Static)
Project Detail | Date
Project Start Date | 2015-12-29
Project End Date
Release 1 - Demo | 2016-01-11
Release 2 - First Domain Deployment

## Resource Management
Category | Resource Name
Web Devlopement | Veena
Review | Ameer
UI Modification | Ameer
Change Request | Mubasshir
Bug Fixes
``

## CR Management
CR Date : 23/01/2016
CR Name | Description | Page/Change Area | Resource | Start Date | End Date | Actual Start Date | Actual End Date | Status | Comments
Text Removal and UI Modification | "We are Kewal Endoscopy Center (bold pink) located in Jalgaon, Maharashtra, specializing in Gynecological laparoscopy, hysteroscopy & infertility. (REMOVE -> )We are licensed by the State of Maharashtra and the Centers for Medicare and Medicaid." | Home Page | Mubasshir | 2016-01-30 | 2016-01-30 |  | 2016-02-02 | Completed
Text Modification | Doctor's Profile : * - Consultant Laparoscopy Surgeon* | Home Page | Mubasshir | 2016-01-30 | 2016-01-30 |  | 2015-12-31 | Completed
Text Removal | (Remove ->) "training schedules for young Endoscopists are also available at the clinic." | About Us | Mubasshir | 2016-01-30 | 2016-01-30 |  | 2015-12-31 | Completed
Menu Removal | (Remove->) All info about ART | Top Navigation | Mubasshir | 2016-01-31 | 2016-01-31 |  | 2016-02-02 | Completed
Menu Addition | Add new Menu : FAQ's and Add all FAQ's from http://laparoscopyexpert.com/faq_for_patient.html | Top Navigation | Mubasshir | 2016-02-01 | 2016-02-03 |  |  | In Progress

## To-Do Tasks
Page | Task
About Us | This page contains Photo Gallery with Dummy Data. Need to put actual data.
News and Press | There are some dummy news and dummy archives on Right Side bar. Need to put actual data.
Testimonials | Contains dummy data. Need to replace with the actual one.
Videos | Contains dummy videos. Need to replace with the actual one.
FAQ | In Progress.
Footer | remove the links for "PINTEREST" and "RSS". Keep only FB, Twitter, & LinkedIn.
Contact US | Current Code is not working. We'll actually deploy & will check if existing code works or not.